## Tracker
Epic JIRA ID | Process Function | Scrum Team | RICEFW Type | RICEFW | WRICEF Name | Common Objects | NEW/Modify/Extend | Priority | Complexity | FD Owner Name / KT POC | Release | Object Type | KT Session ID | KT Date | Criticality (1–5) | Complexity (1–5) | Tier 1 Override (Y/N) | Risk Score | Risk Band | Tier | P1 Monitoring & Observability | P2 Exception & Error Handling | P3 Supportability | P4 Knowledge & AMS Readiness | P5 Prevention & Recovery | P6 Security & Access | Readiness Avg | Lowest Pillar | Weakest-Link Cap | Readiness Band | Heat Map Status | Gap Description | Action | Project Owner | Due Date | Gap Status | AMS Scorer | AMS Scored On | Project Response Due | Project Status | Effective Project Status | TPO Confirmed (Y/N) | TPO Confirmed On | Rescore Date | Comments
JGHJ-47410 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-47410 | Commercial-Batch Master Data Interface - KDC | Not a Common Object | WRICEF-NEW | Critical | Complex | Amey/ Tilak | R2.2
JGHJ-55099 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55099 | Commercial-Batch Master Data Interface - FDC | Not a Common Object | No release build scope | Critical | Complex | Amey/ Tilak | R2.2
JGHJ-55210 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55210 | Commercial- Purchase Order Interface - KDC | R2.2 Common Object - LOG-55210 & LOG-55211 | WRICEF-NEW | Critical | Complex | Amey/ Tilak | R2.2
JGHJ-55211 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55211 | Commercial- Purchase Order Interface - FDC | R2.2 Common Object - LOG-55210 & LOG-55211 | WRICEF-REUSE-EXTEND | Critical | Complex | Amey/ Tilak | R2.2
JGHJ-36360 | IMT-LOGISTICS | TM_TIME_IM | Enhancement | DEL-421 | XPS Integraion - Update Tracking Number into Deliveries . (XPS) | R1 & R2.2 Common Object - DEL-421 | WRICEF-MODIFY | Critical | Medium | Raghuma Busireddy | R2.2
JGHJ-52471 | IMT-LOGISTICS | TM_TIME_IM | Enhancement | LOG-52471 | TIME-L3-LOG-TM-E Allow Insourced and Outsourced from same shipping point | Not a Common Object | WRICEF-NEW | Critical | Medium | Vishwanath Hunnur | R2.2
JGHJ-55233 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55233 | Commercial-Batch creation for Non ASN customers from BY to TIME-KDC | R2.2 Common Object - LOG-55233 & LOG-55234 | WRICEF-MODIFY | Critical | High | Amey/ Tilak | R2.2
JGHJ-55234 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55234 | Commercial-Batch creation for Non ASN customers from BY to TIME-FDC | R2.2 Common Object - LOG-55233 & LOG-55234 | WRICEF-REUSE-EXTEND | Critical | High | Amey/ Tilak | R2.2
JGHJ-55222 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55222 | Commercial - Inventory Snapshot from Non-SAP WMS Inventory Balance Sync - KDC | Not a Common Object | WRICEF-NEW | Critical | High | Amey/ Tilak | R2.2
JGHJ-55225 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55225 | Commercial - Inventory Snapshot from Non-SAP WMS Inventory Balance Sync - FDC | Not a Common Object | Reuse-Extend | Critical | Complex | Amey/ Tilak | R2.2
JGHJ-55241 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55241 | Commercial-Ext Wh Integration (Non-SAP WMS)- Delivery Note Comparison Interface(delivery Sync)- KDC | Not a Common Object | WRICEF-NEW | Critical | High | Amey/ Tilak | R2.2
JGHJ-55244 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55244 | Commercial-Ext Wh Integration (Non-SAP WMS)- Delivery Note Comparison Interface(delivery Sync)- FDC | Not a Common Object | WRICEF-NEW | Critical | Complex | Amey/ Tilak | R2.2
JGHJ-57111 | IMT-LOGISTICS | INVM_TIME_IM | Enhancement | LOG-57111 | Ext Wh Integration (Non-SAP WMS)- Delivery Note Comparison Enhancement (delivery Sync)- Both Supporting Commercial and Clinical Deliveries | Not a Common Object | WRICEF-NEW | High | High | Amey/ Tilak | R2.2
JGHJ-55135 | IMT-RESEARCH_DEVELOPMENT | R&D_TIME_IM | Enhancement | R&D-55135 | R & D - PO creation to receive CFG in FDC from Beerse | With SAP | WRICEF-NEW | High | High | R&D Team | R2.2
JGHJ-36220 | IMT-LOGISTICS | TM_TIME_IM | Enhancement | DEL-054 | Pass the Transportation specific Information from the Delivery to XPS system. | R1 & R2.2 Common Object - DEL-054 | WRICEF-MODIFY | Medium | Low | Vishwanath Hunnur | R2.2
JGHJ-72245 | IMT-LOGISTICS | TM_TIME_IM | Interface | LOG-72245 | Void Label - FDC | R2.2 Common Object - LOG-72245 & LOG-72246 | WRICEF-MODIFY | Medium | Medium | Raghuma Busireddy | R2.2
JGHJ-72246 | IMT-LOGISTICS | TM_TIME_IM | Interface | LOG-72246 | Void Label - KDC | R2.2 Common Object - LOG-72245 & LOG-72246 | WRICEF-MODIFY | Medium | Medium | Raghuma Busireddy | R2.2
JGHJ-36543 | IMT-MASTER_DATA | MDG_TIME_IM | Enhancement | MDG-M-007 | MDG-M-007 Material Data Model Enhancement | R1, R2.2 & R3.1 Common Object - MDG-M-007, MDG-M-007A, MDG-M-007B | WRICEF-MODIFY | High | High | Pritam/Onkar/Prajakta | R2.2 | Enhancement | KT-01 | 2026-09-15 | 2 | 2 | Y | 4 | Low | Tier 1 | 2 | 4 | 2 | 4 | 4 | 4 | 3.3 | 2 | Yes | Medium | Controlled | P1 - This RICEFW is specific to MDG Material data model extension under Material and UOM entity. No automated alerts are configured. P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | MDG Team |  | Closed | MDG Lead | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-36549 | IMT-MASTER_DATA | MDG_TIME_IM | Enhancement | MDG-M-013 | UI Modification - Material | R1, R2.2 & R3.1 Common Object - MDG-M-013 | WRICEF-MODIFY | Medium | Medium | Pritam/Onkar/Prajakta | R2.2 | Enhancement | KT-01 | 2026-09-15 | 2 | 2 | Y | 4 | Low | Tier 1 | 2 | 4 | 2 | 4 | 4 | 4 | 3.3 | 2 | Yes | Medium | Controlled | P1 - This RICEFW is specific to MDG Material UI Enhancement for Material and UOM entity. No automated alerts are configured. P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | MDG Team |  | Closed | MDG Lead | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-46468 | IMT-MAKE | QUALITY_TIME_IM | Interface | MAK-46468 | Arctic to SAP system - Interface to support BOM FID functionality. | Not a Common Object | WRICEF-NEW | Medium | Medium | Giusy/Monica | R2.2 | Integration (BTP IS) | QM KT-02 | 2026-09-21 | 3 | 3 |  | 9 | Moderate | Tier 2 | 4 | 4 | 2 | 4 | 4 | 3 | 3.5 | 2 | Yes | Medium | Monitor | P3--No Runbook available P6--AMS access requirements are identified; however, complete documentation are not fully available. |  |  |  |  | AMS Lead(Shashi) | 2026-09-29 | 2026-10-02 | Pending | Deemed confirmed | N
JGHJ-53886 | IMT-MAKE | QUALITY_TIME_IM | Enhancement | MAK-53886 | Link Quality Notification to impacted batches (BUS JGFY-9485) | Not a Common Object | WRICEF-NEW | Medium | Medium | Giusy/Monica | R2.2 | Enhancement | QM KT-03 | 2026-09-23 | 1 | 2 |  | 2 | Low | Tier 3 | 2 | 3 | 4 | 4 | 4 | 4 | 3.5 | 2 | Yes | Medium | Controlled | P1-- Still no automatic alert mechanism (e.g mail notification for failure) is available. |  | Project Team(Harad,Ajit) |  |  | AMS Lead(Shashi) | 2026-09-29 | 2026-10-02 | Pending | Deemed confirmed | N
JGHJ-53875 | IMT-MAKE | QUALITY_TIME_IM | Enhancement | MAK-53875 | Prevent SLED update at DC | Not a Common Object | WRICEF-NEW | Medium | Medium | Jayavibhava | R2.2
JGHJ-55223 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55223 | Clinical - Inventory Snapshot from Non-SAP WMS Inventory Balance Kitted Sync - KDC | Not a Common Object | Reuse-Extend | Medium | High | Amey/ Tilak | R2.2
JGHJ-55224 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55224 | Clinical - Inventory Snapshot from Non-SAP WMS Inventory Balance Kitted Sync - FDC | Not a Common Object | WRICEF-NEW | High | High | Amey/ Tilak | R2.2
JGHJ-51383 | IMT-MAKE | QUALITY_TIME_IM | Enhancement | MAK-51383 | Store and Maintain artwork data (from Arctic) and CMO artwork data in TIME to process artwork management | Not a Common Object | WRICEF-NEW | High | High | Giusy/Monica | R2.2 | Integration (BTP IS)
JGHJ-55229 | IMT-MASTER_DATA | MDG_TIME_IM | Interface | MDG-V-55229 | Inbound Interface from GSDB to MDG for Vendor Creation | R1 & R2.2 Common Object - MDG-C-006, MDG-C-027 | WRICEF-MODIFY | Medium | High | Guru Chaitanya/Mohit | R2.2
JGHJ-36564 | IMT-MASTER_DATA | MDG_TIME_IM | Workflow | MDG-C-032 | Create Customer Workflow & Dynamic Workflow Routing | R1 & R2.2 Common Object - MDG-C-001, MDG-M-024, MDG-C-030, MDG-C-032 | WRICEF-MODIFY | Medium | Medium | Guru Chaitanya/Mohit | R2.2 | Workflow | KT-01 | 2026-09-08 | 3 | 2 | Y | 6 | Low | Tier 1 | 3 | 3 | 2 | 4 | 4 | 4 | 3.3 | 2 | Yes | Medium | Controlled | P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | MDG Team |  | Closed |  | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-42596 | IMT-LOGISTICS | TM_TIME_IM | Enhancement | DEL-621 | Retrigger sending delivery details to GW based on delivery changes | R1 & R2.2 Common Object - DEL-621 | WRICEF-MODIFY | Medium | Medium | Vishwanath Hunnur | R2.2
JGHJ-43580 | IMT-MAKE | QUALITY_TIME_IM | Report | MAK-5096 | Controlled Substance Summary report | R1 & R2.2 Common Object - MD-0118, MAK-1084 | WRICEF-MODIFY | Medium | Medium | Jayavibhava | R2.2
JGHJ-55235 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55235 | Wave Planning interface from BY to TIME - FDC | R2.2 Common Object - LOG-55235 & LOG-55236 | WRICEF-MODIFY | Medium | High | Amey/ Tilak | R2.2
JGHJ-55236 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55236 | Wave Planning interface from BY to TIME - KDC | R2.2 Common Object - LOG-55235 & LOG-55236 | WRICEF-MODIFY | Medium | High | Amey/ Tilak | R2.2
JGHJ-46460 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-46460 | Inbound Contract Prices from Model-N to S4 | Not a Common Object | WRICEF-NEW | Medium | Low | Dhaval | R2.2 | Interface (IDoc/Proxy/API) | KT-01 | 2026-09-15 | 4 | 4 | Y | 16 | High | Tier 1 | 5 | 5 | 5 | 5 | 4 | 5 | 4.8 | 4 | No | High | Controlled | BTP will get the system generated incident which needs to be analyzed BTP and S/4 CE team for resolution | Need colaboration with BTP and business master data team for error resolution | CE Team |  | Closed | AMS CE Lead | 2026-09-24 | 2026-09-29 | Pending | Deemed confirmed
JGHJ-55219 | IMT-PLAN_SOURCE | PLAN_TIME_IM | Interface | PLN-55219 | Integrate Artwork ID from Atlas to Time | Not a Common Object | WRICEF-NEW | Medium | Medium | Reddy, Gopinatha | R2.2
JGHJ-53880 | IMT-GTS | GTS_TIME_IM | Enhancement | GTS-53880 | Automatic Upload of SPL and Classification Files to GTS | Not a Common Object | WRICEF-NEW | Medium | High | RMada@ITS.JNJ.com/Spradh26@its.jnj.com | R2.2
JGHJ-36215 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Enhancement | DEL-022 | DEL-022 - Sales Order Billing Blocks | R1 & R2.2 Common Object - DEL-022, DEL-023, DEL-025 | WRICEF-MODIFY | Medium | Medium | Santhosh/Vaishnav | R2.2
JGHJ-36216 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Report | DEL-023 | Return Authorization Approval Worklist (formerly: Returns Approval Workflow) | R1 & R2.2 Common Object - DEL-022, DEL-023, DEL-025 | WRICEF-MODIFY | Medium | High | Quinn | R2.2
JGHJ-54732 | IMT-MAKE | SUST_TIME_IM | Interface | MAK-54732 | DG office document as attachment to Freight Order and Storage in Open Text | Not a Common Object | WRICEF-NEW | High | High | Perri, Alessandra | R2.2
JGHJ-51403 | IMT-PLAN_SOURCE | PLAN_TIME_IM | Interface | PLN-51403 | Integrate Artwork ID from Time to EU2 | Not a Common Object | WRICEF-NEW | Medium | Medium | Solanki, Abhimanyu | R2.2
JGHJ-55230 | IMT-MASTER_DATA | MDG_TIME_IM | Interface | MDG-C-55230 | Inbound Interface from MDM to MDG (MDC) | Not a Common Object | WRICEF-NEW | Medium | Medium | Guru Chaitanya/Mohit | R2.2 | Interface (IDoc/Proxy/API) | KT-03 | 2026-09-10 | 3 | 4 | N | 12 | Moderate | Tier 2 | 2 | 3 | 2 | 4 | 4 | 4 | 3.2 | 2 | Yes | Medium | Monitor | P1 - This RICEFW is specific to Customer Interface from CODI - BTP - MDG. Alerts will be notified to BTP and MDG can look into proxy logs P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | MDG Team |  | Closed |  | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-47419 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-47419 | Product Flow Creation/Upload/Validation | R2.1 & R2.2 Common Object - VCM-47419 | WRICEF-MODIFY | Medium | Medium | Pratiksha | R2.2
JGHJ-55137 | IMT-MASTER_DATA | MDG_TIME_IM | Workflow | MDG-V-55137 | MDG - Create Vendor Workflow & Dynamic Routing | Not a Common Object | WRICEF-NEW | High | High | Harsh Arora/Prajakta | R2.2
JGHJ-55141 | IMT-MASTER_DATA | MDG_TIME_IM | Workflow | MDG-V-55141 | MDG- Exceptional Vendor Create Workflow | Not a Common Object | WRICEF-NEW | Low | Low | Harsh Arora/Prajakta | R2.2
JGHJ-55142 | IMT-MASTER_DATA | MDG_TIME_IM | Workflow | MDG-V-55142 | MDG- Exceptional Vendor Change Workflow | Not a Common Object | WRICEF-NEW | Low | Low | Harsh Arora/Prajakta | R2.2
JGHJ-55153 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-55153 | Product Flow Lane master data health monitoring (Lane Health) | Not a Common Object | WRICEF-NEW | High | High | Sarang Niwal | R2.2
JGHJ-47417 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-47417 | TIME-L3-LOG-TM Store external documents into Delivery - shipping documents (Packing List) from BY and store on OT DMS - KDC | Not a Common Object | WRICEF-NEW | Medium | High | Amey/ Tilak | R2.2
JGHJ-55105 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55105 | TIME-L3-LOG-TM Store external documents into Delivery - shipping documents (Packing List) from BY and store on OT DMS - FDC | Not a Common Object | WRICEF-NEW | Medium | High | Amey/ Tilak | R2.2
JGHJ-46449 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-46449 | Outbound Return Order from S4 to Model-N | Not a Common Object | WRICEF-NEW | Medium | Medium | Dhaval | R2.2
JGHJ-47370 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Enhancement | DEL-47370 | Copy Control From Billing Document to Sales Order (Credit Memo / Return Order) | Not a Common Object | WRICEF-NEW | Medium | Medium | Santhosh | R2.2
JGHJ-36224 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Report | DEL-135 | Report on Price Condition change | R1 & R2.2 Common Object - DEL-135, DEL-619 | WRICEF-MODIFY | High | High | Vaishnav | R2.2 | Report | KT-01 | 2026-09-15 | 2 | 2 | Y | 4 | Low | Tier 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | No | High | Controlled | No Gaps Indentified as it is existing report from R1 only background functionality has been added in R2.2 | Regular Incident Resolution | CE Team |  | Closed | AMS Lead | 2026-09-24 | 2026-09-29 | Pending | Deemed confirmed
JGHJ-52181 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Enhancement | DEL-52181 | Interface from BTP to TIME - Average WAC Calculation | Not a Common Object | WRICEF-NEW | High | High | Dinesh | R2.2
JGHJ-52474 | IMT-LOGISTICS | INVM_TIME_IM | Enhancement | LOG-52474 | Disable WMS delivery updates when a Wave is Planned for outbound deliveries in BY | Not a Common Object | WRICEF-NEW | High | High | Amey/ Tilak | R2.2
JGHJ-53888 | IMT-GTS | GTS_TIME_IM | Enhancement | GTS-53888 | TIME-L3-GTS-GT HTS Code Check during Sales Order Creation | Not a Common Object | WRICEF-NEW | High | High | RMada@ITS.JNJ.com/Spradh26@its.jnj.com | R2.2
JGHJ-69321 | IMT-MASTER_DATA | MDG_TIME_IM | Interface | MDG-C-69321 | Outbound Interface from TIME S/4 to MDM | Not a Common Object | WRICEF-NEW | High | High | Guru Chaitanya/Mohit | R2.2 | Interface (IDoc/Proxy/API) | KT-03 | 2026-09-10 | 2 | 2 | N | 4 | Low | Tier 3 | 2 | 1 | 2 | 4 | 4 | 4 | 2.8 | 1 | Yes | Low | Monitor | P1 - This RICEFW is specific to Customer Interface S4 - BTP. No action needed from MDG AMS. P2 - No Error Handling monitoring will be done from MDG AMS. P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | MDG Team |  | Closed |  | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-71299 | IMT-MAKE | QUALITY_TIME_IM | Interface | MAK-71299 | BOM FID - TIME-ATLAS interfaces for Artwork consumptions | Not a Common Object | WRICEF-NEW | Medium | Medium | Giusy/Monica | R2.2
JGHJ-36423 | IMT-FINANCE | FI_GLINTEGRATION_TIME_IM | Interface | FIN-0038 | Outbound Interface needed for Signifi/CFIN Data sending customer information to CFIN (MD) | R1 & R2.2 Common Object - FIN-0038 | WRICEF-MODIFY-EXTEND | Medium | Medium | Bhanu/Swapnil | R2.2
JGHJ-36540 | IMT-MASTER_DATA | MDG_TIME_IM | Enhancement | MDG-M-36540 | Material Data Validations and Derivations1 | R1, R2.1, R2.2 & R3.1 Common Object - MDG-M-011, MDG-M-011A, MDG-M-010 | WRICEF-MODIFY | Medium | Medium | Pritam/Onkar/Prajakta | R2.2
JGHJ-36547 | IMT-MASTER_DATA | MDG_TIME_IM | Enhancement | MDG-C-013 | UI Modification - Customer | R1, R2.1 & R2.2 Common Object - MDG-C-013, MDG-C-006, MDG-C-027 | WRICEF-MODIFY | Medium | Medium | Poorna/Mohit | R2.2 | Enhancement | KT-02 | 2026-09-09 | 2 | 2 | Y | 4 | Low | Tier 1 | 2 | 4 | 2 | 5 | 4 | 4 | 3.5 | 2 | Yes | Medium | Controlled | P1 - This RICEFW is specific to MDG Customer UI Extension for ICSM section UIBB. No automated alerts are configured. P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | MDG Team |  | Closed |  | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-36542 | IMT-MASTER_DATA | MDG_TIME_IM | Enhancement | MDG-C-006 | MDG-C-006 Customer Validations and Derivations 1 | R1, R2.1 & R2.2 Common Object - MDG-C-006, MDG-C-027 | WRICEF-MODIFY | High | High | Poorna/Mohit | R2.2 | Enhancement | KT-01 | 2026-09-08 | 3 | 2 | Y | 6 | Low | Tier 1 | 2 | 4 | 2 | 4 | 4 | 4 | 3.3 | 2 | Yes | Medium | Controlled | P1 - This RICEFW is specific to MDG Customer Validations & Derivations. No automated alerts are configured. P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | MDG Team |  | Closed |  | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-71303 | IMT-MAKE | QUALITY_TIME_IM | Interface | MAK-71303 | BOM FID - TIME-EUR2 interfaces for Artwork consumptions | Not a Common Object | WRICEF-NEW | Medium | Medium | Giusy/Monica | R2.2
JGHJ-36277 | IMT-MAKE | QUALITY_TIME_IM | Enhancement | MAK-1009 | MAK-1009 Deadline Monitoring | R1 & R2.2 Common Object - MAK-1009 | WRICEF-MODIFY | Medium | Low | Giusy/Monica | R2.2
JGHJ-51374 | IMT-GTS | GTS_TIME_IM | Enhancement | GTS-51374 | Product Classification Using Input File | Not a Common Object | WRICEF-NEW | High | High | RMada@ITS.JNJ.com/Spradh26@its.jnj.com | R2.2 | [21 empty] | 2. Confirm alignment with the design document for Customer Create, Change, and Extension processes.
JGHJ-46459 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-46459 | Outbound List Price from S4 to Model-N | Not a Common Object | WRICEF-NEW | Medium | Medium | Dhaval | R2.2 | Interface (IDoc/Proxy/API) | KT-01 | 2026-09-15 | 4 | 4 | Y | 16 | High | Tier 1 | 5 | 5 | 5 | 5 | 4 | 5 | 4.8 | 4 | No | High | Controlled | BTP will get the system generated incident which needs to be analyzed BTP and S/4 CE team for resolution | 3. Validate mandatory fields, formatting checks, and conditional derivations. | CE Team |  | Closed | AMS CE Lead | 2026-09-24 | 2026-09-29 | Pending | Deemed confirmed
JGHJ-76006 | IMT-VALUE_CHAIN | VCM_TIME_IM | Report | VCM-76006 | VCM Error Log Report | Not a Common Object | WRICEF-NEW | High | High | Aditya malkoti | R2.2 | [21 empty] | 4. Ensure rule execution is correct by account group, sales area, country, and customer type.
JGHJ-76590 | IMT-RESEARCH_DEVELOPMENT | R&D_TIME_IM | Interface | R&D-76590 | R & D - Study Master Report Upload to DMS | With SAP | WRICEF-NEW | Medium | Medium | R&D Team | R2.2 | [21 empty] | 5. Test key default derivations, including tax classification, BP roles, reconciliation accounts, and payment terms.
JGHJ-50982 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-50982 | Call to ATTP to validate the Serial Number coming from the return order | Not a Common Object | WRICEF-NEW | High | High | Dinesh | R2.2 | [21 empty] | 6. Review and incorporate any post-design changes.
JGHJ-70302 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-70302 | AT Excecption 2 - Backup (Retain) Bag Shipment | Not a Common Object | WRICEF-NEW | Medium | Medium | Rashmi Krishnappa | R2.2
JGHJ-55139 | IMT-MASTER_DATA | MDG_TIME_IM | Workflow | MDG-V-55139 | MDG- Extend Vendor Workflow & Dynamic Routing | Not a Common Object | WRICEF-NEW | Medium | Medium | Harsh Arora/Prajakta | R2.2
JGHJ-55138 | IMT-MASTER_DATA | MDG_TIME_IM | Workflow | MDG-V-55138 | MDG - Change Vendor Workflow & Dynamic Routing | Not a Common Object | WRICEF-NEW | High | High | Harsh Arora/Prajakta | R2.2
JGHJ-54696 | IMT-LOGISTICS | INVM_TIME_IM | Report | LOG-54696 | Shipping Expiry report | Not a Common Object | WRICEF-NEW | Medium | High | Amey/ Tilak | R2.2
JGHJ-36221 | IMT-LOGISTICS | TM_TIME_IM | Enhancement | DEL-055 | Update Carrier information determined by XPS to S4 HANA Delivery. | R1 & R2.2 Common Object - DEL-081, DEL-087, DEL-055, DEL-055A | WRICEF-MODIFY | Medium | Low | Raghuma Busireddy Vishwanath Hunnur | R2.2
JGHJ-76505 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Enhancement | DEL-76505 | Additional Delivery Information to ATTP | Not a Common Object | WRICEF-NEW | Medium | Medium | Dinesh | R2.2
JGHJ-36403 | IMT-LOGISTICS | TM_TIME_IM | Enhancement | DEL-701 | Carrier Requirement Table | R1 & R2.2 Common Object - DEL-701, DEL-TBD-010 | WRICEF-MODIFY | Medium | High | Raghuma Busireddy | R2.2
JGHJ-51414 | IMT-PLAN_SOURCE | SOURCE_TIME_IM | Interface | SOU-51414 | Inbound SO Confirmation from ATLAS to update PO in TIME | Not a Common Object | WRICEF-NEW | Medium | Medium | Prasad, Vara | R2.2
JGHJ-51415 | IMT-PLAN_SOURCE | SOURCE_TIME_IM | Interface | SOU-51415 | Inbound SO Confirmation from SUSTAIN to update PO in TIME | Not a Common Object | WRICEF-NEW | Medium | Medium | Prasad, Vara | R2.2
JGHJ-54626 | IMT-LOGISTICS | TM_TIME_IM | Interface | LOG-54626 | TIME-L3-LOG-TM World courier carrier integration | Not a Common Object | WRICEF-NEW | Medium | Medium | Raghuma Busireddy | R2.2
JGHJ-52473 | IMT-LOGISTICS | TM_TIME_IM | Enhancement | LOG-52473 | TIME-L3-LOG-TM Tracking number update in parcel tracking tab for BY deliveries after package creation initiated in BY | Not a Common Object | WRICEF-NEW | Medium | Medium | Raghuma Busireddy | R2.2
JGHJ-55103 | IMT-LOGISTICS | TM_TIME_IM | Enhancement | LOG-55103 | TIME-L3-LOG-TM-E FDC & KDC Charge updates in Freight Order | Not a Common Object | WRICEF-NEW | Medium | Medium | Zahabiya Valigi | R2.2
JGHJ-36550 | IMT-MASTER_DATA | MDG_TIME_IM | Enhancement | MDG-M-003 | MDG-M-003 Material Custom Table for dependency and critical fields | R1 & R2.2 Common Object - MDG-M-003, MDG-M-003B | WRICEF-MODIFY | Medium | Medium | Pritam/Onkar/Prajakta | R2.2
JGHJ-55207 | IMT-MASTER_DATA | MDG_TIME_IM | Interface | MDG-C-55207 | R & D Customer Master interface from CODI | Not a Common Object | WRICEF-NEW | Medium | Complex | Guru Chaitanya/Mohit | R2.2 | Interface (IDoc/Proxy/API) | KT-03 | 2026-09-10 | 3 | 4 | N | 12 | Moderate | Tier 2 | 2 | 3 | 2 | 4 | 4 | 4 | 3.2 | 2 | Yes | Medium | Monitor | P1 - This RICEFW is specific to Customer Interface from CODI - BTP - MDG. Alerts will be notified to BTP and MDG can look into SOA logs. P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | MDG Team |  | Closed |  | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-53827 | IMT-FINANCE | FI_PCIV_TIME_IM | Report | FIN-53827 | SLOB(Slow and obsolete inventory) report out | Not a Common Object | WRICEF-NEW | Medium | Low | Satish Sanka | R2.2 | [20 empty] | P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS.
JGHJ-46463 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-46463 | Inbound Return Order pricing from Model-N to S4 | Not a Common Object | WRICEF-NEW | Medium | Medium | Dhaval | R2.2
JGHJ-57108 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Enhancement | DEL-57108 | Copy Custom Field Values From Sales Order / Delivery to Invoice | Not a Common Object | WRICEF-NEW | Medium | Medium | Santhosh | R2.2
JGHJ-73641 | IMT-FINANCE | FI_GLINTEGRATION_TIME_IM | Enhancement | FIN-73641 | Update final invoice indicator on PO | Not a Common Object | WRICEF-NEW | Medium | Medium | Swapnil/Bhanu | R2.2
JGHJ-72011 | IMT-MAKE | QUALITY_TIME_IM | Interface | MAK-72011 | Comet Interface for Open NC/CC | Not a Common Object | WRICEF-NEW | Medium | Low | Giusy/Monica | R2.2
JGHJ-76201 | IMT-MASTER_DATA | MDG_TIME_IM | Enhancement | MD-76201 | New RICEFW for Enhancement CODI Interface | Not a Common Object | WRICEF-NEW | Medium | Medium | Guru Chaitanya/Mohit | R2.2 | Enhancement | KT-03 | 2026-09-10 | 3 | 3 | N | 9 | Moderate | Tier 2 | 2 | 3 | 2 | 4 | 4 | 4 | 3.2 | 2 | Yes | Medium | Monitor | P1 - This RICEFW is specific to Customer enhancement from CODI - BTP - MDG. Alerts will be notified to BTP and MDG can look into SOA logs. | No runbook is defined for this RICEFW. | MDG Team |  | Closed |  | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-76523 | IMT-LOGISTICS | LOG_IO_TIME_IM | Enhancement | LOG-76523 | CMO Batch Inbound Delivery Update during Goods Receipt | Not a Common Object | WRICEF-NEW | Medium | Medium | Gottipati, Buchi Babu | R2.2 | [20 empty] | P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS.
JGHJ-55151 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-55151 | Scenario Determination | R2.1 & R2.2 Common Object - VCM-55151 | WRICEF-MODIFY | Medium | Medium | Pratiksha | R2.2
JGHJ-55144 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-55144 | Cancellation of documents in automation | Not a Common Object | WRICEF-NEW | High | High | Rashmi Krishnappa | R2.2
JGHJ-74600 | IMT-MASTER_DATA | MDG_TIME_IM | Interface | MD-74600 | R & D Update Customer Master interface from CODI | Not a Common Object | WRICEF-NEW | Medium | Medium | Guru Chaitanya/Mohit | R2.2 |  | KT-03 | 2026-09-10 | 3 | 4 | N | 12 | Moderate | Tier 2 | 2 | 3 | 2 | 4 | 4 | 4 | 3.2 | 2 | Yes | Medium | Monitor | P1 - This RICEFW is specific to Customer Interface from CODI - BTP - MDG. Alerts will be notified to BTP and MDG can look into SOA logs. P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | MDG Team |  | Closed |  | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-72029 | IMT-MAKE | QUALITY_TIME_IM | Report | MAK-72029 | QP Release in 2.2 and Batch Release Register | Not a Common Object | WRICEF-NEW | Medium | Medium | Giusy/Monica | R2.2 | Report | QM KT-03 | 2026-09-23 | 1 | 2 |  | 2 | Low | Tier 3 | 2 | 1 | 3 | 3 | 4 | 1 | 2.3 | 1 | Yes | Low | Monitor | P1-- Still no automatic alert mechanism (e.g mail notification for failure) is available. P2 - There is no failure msg retriving |  | Project Team(Raho, Giusy) |  | Open | AMS Lead(Shashi) | 2026-09-28 | 2026-10-01 | Pending | Deemed confirmed | N
JGHJ-47416 | IMT-MAKE | QUALITY_TIME_IM | Enhancement | MAK-47416 | BOM FID - Batch status auto-update after stock blocking | Not a Common Object | WRICEF-NEW | Medium | Medium | Giusy/Monica | R2.2
JGHJ-47421 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-47421 | Delivery Request (Shipment) Creation - Trigger from PO | R2.1 & R2.2 Common Object - VCM-47421, VCM-55152, VCM-55155, VCM-76007 | WRICEF-MODIFY | High | High | Pravin Padwal | R2.2
JGHJ-55152 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-55152 | Master Data Check | R2.1 & R2.2 Common Object - VCM-47421, VCM-55152, VCM-55155, VCM-76007 | WRICEF-MODIFY | Medium | Medium | Sarang Niwal | R2.2
JGHJ-36398 | IMT-LOGISTICS | LOG_IO_TIME_IM | Enhancement | DEL-109 | E2E Orchestration Application (Formerly: CAR-T / Advanced Therapies Journey Status Monitoring W1/R1/MVP) | R1, R2.1 & R2.2 Common Object - DEL-109 | WRICEF-MODIFY | Medium | Medium | Gottipati, Buchi Babu | R2.2
JGHJ-78175 | IMT-PLAN_SOURCE | SOURCE_TIME_IM | Interface | SOU-78175 | Send GR in FDC to EU2 to create a late PO (Consignment PO) | Not a Common Object | WRICEF-NEW | Medium | Medium | Poman, Vikas | R2.2
JGHJ-52179 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-52179 | Outbound Order Acknowledgment - EDI 855 | R1, R2.1 & R2.2 Common Object - DEL-52179, DEL-52179 & DEL-78694 | WRICEF-MODIFY | High | High | Santhosh | R2.2
JGHJ-78694 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-78694 | Credit/Debit Memo Request Acknowledgement from TIME to EXA | R2.2 Common Object - DEL-52179 & DEL-78694 | WRICEF-MODIFY | Medium | Medium | Setu/Dinesh | R2.2
JGHJ-71440 | IMT-MAKE | QUALITY_TIME_IM | Interface | MAK-71440 | Inspection Lot update and Stock Posting of Damaged Inbound triggered by Blue Yonder | Not a Common Object | WRICEF-NEW | Medium | Medium | Giusy/Monica | R2.2
JGHJ-53890 | IMT-LOGISTICS | LOG_IO_TIME_IM | Interface | LOG-53890 | Inbound ASN Interface from ATLAS to create Inbound delivery in TIME | R2.1 & R2.2 Common Object - LOG-53890 & LOG-53892 | WRICEF-MODIFY | Medium | Medium | Kumar maddela, Naveen | R2.2
JGHJ-53892 | IMT-LOGISTICS | LOG_IO_TIME_IM | Interface | LOG-53892 | Inbound ASN Interface from SUSTAIN to create Inbound delivery in TIME | R2.1 & R2.2 Common Object - LOG-53890 & LOG-53892 | WRICEF-MODIFY | Medium | Medium | Kumar maddela, Naveen | R2.2
JGHJ-55216 | IMT-LOGISTICS | LOG_IO_TIME_IM | Interface | LOG-55216 | Clinical IBD For OUS Shipment interface from S4 Time to EU2 | R1, R2.1 & R2.2 Common Object - LOG-55216 | WRICEF-MODIFY | Medium | Medium | Gottipati, Buchi Babu | R2.2
JGHJ-54733 | IMT-LOGISTICS | TM_TIME_IM | Interface | LOG-54733 | Send shipping details to DG Office to generate DG document | Not a Common Object | WRICEF-NEW | High | High | Vishwanath Hunnur | R2.2
JGHJ-46466 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-46466 | Outbound Invoice to Model-N for Government Sales | R1, R2.1 & R3.1 Common Object - MD-0288, DEL-78693, FIN-0063A | WRICEF-MODIFY | Medium | Medium | Dhaval | R2.2
JGHJ-53881 | IMT-GTS | GTS_TIME_IM | Enhancement | GTS-53881 | Provide classification and license data to S/4 from GTS | Not a Common Object | WRICEF-NEW | Medium | High | RMada@ITS.JNJ.com/Spradh26@its.jnj.com | R2.2
JGHJ-36349 | IMT-FINANCE | FI_GLINTEGRATION_TIME_IM | Enhancement | FIN-0002 | TIME-FIN-ENH-FI CAT CO EXT FIN-0002 R2.2 | R1, R2.1 & R2.2 Common Object - FIN-0002 | WRICEF-MODIFY | Medium | Medium | Swapnil/Rohit | R2.2
JGHJ-77483 | IMT-FINANCE | FI_GLINTEGRATION_TIME_IM | Enhancement | FIN-77483 | Substitution to determine Partner and Profit Center on JOM Control/CICO Account | R1 & R2.1 Common Object - FIN-002, FIN-47374, FIN-77483 | WRICEF-MODIFY | Medium | Medium | Swapnil/Rohit | R2.2
JGHJ-36228 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Form | DEL-201 | Commercial Invoice Form | R1, R2.1 & R2.2 Common Object - DEL-201, DEL-524, DEL-342, DEL-184, DEL-52177 | WRICEF-MODIFY | Medium | Medium | Santhosh/Setu | R2.2 | Form | KT-02 | 2026-09-21 | 2 | 2 | Y | 4 | Low | Tier 1 | 3 | 4 | 5 | 5 | 5 | 4 | 4.3 | 3 | No | High | Controlled | No gaps identified. In case of error, then output reprocess required | No gaps identified. In case of error, then output reprocess required
JGHJ-36227 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Form | DEL-524 | Invoice Form in English for CA | R1, R2.1 & R2.2 Common Object - DEL-201, DEL-524, DEL-342, DEL-184, DEL-52177 | WRICEF-MODIFY | Medium | Medium | Santhosh/Setu | R2.2
JGHJ-52177 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Enhancement | DEL-52177 | GTS Call for Licenses and HS Code | R1, R2.1 & R2.2 Common Object - DEL-201, DEL-524, DEL-342, DEL-184, DEL-52177 | WRICEF-MODIFY | Medium | Medium | Firdaus | R2.2
JGHJ-36544 | IMT-MASTER_DATA | MDG_TIME_IM | Enhancement | MDG-C-007 | TIME-L3-MDA-CU-E MDG-C Customer Email Notification_Workflow Notification | R1 & R2.2 Common Object - MDG-C-007 | WRICEF-MODIFY | Medium | Medium | Guru Chaitanya/Mohit | R2.2 | Enhancement | KT-01 | 2026-09-08 | 2 | 2 | Y | 4 | Low | Tier 1 | 2 | 4 | 2 | 4 | 4 | 4 | 3.3 | 2 | Yes | Medium | Controlled | P1 - This RICEFW is specific to MDG Customer Email Notifications. As per the MDG Governance Process, email notifcations for MDG CRs are configured based on the respective personas. P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | MDG Team |  | Closed |  | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-78155 | IMT-GTS | GTS_TIME_IM | Enhancement | GTS-78155 | TIME-L3-GTS-GT Mass Upload of Licenses into GTS | Not a Common Object | WRICEF-NEW | Medium | Medium | RMada@ITS.JNJ.com/Spradh26@its.jnj.com | R2.2 | [20 empty] | P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS.
JGHJ-42579 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Enhancement | DEL-081 | Sales Order - Additional Fields | R1, R2.1 & R2.2 Common Object - DEL-016, DEL-002A, DEL-081, DEL-528 | WRICEF-MODIFY | Medium | Medium | Santhosh | R2.2
JGHJ-36566 | IMT-MASTER_DATA | MDG_TIME_IM | Workflow | MDG-M-037 | Create Material Workflow & Dynamic Workflow Routing - All Stage Gates | R1, R2.1, R2.2 & R3.1 Common Object - MDG-M-037, MDG-M-002, MDG-M-004 | WRICEF-MODIFY | Medium | Medium | Pritam/Onkar/Prajakta | R2.2 | Workflow | KT-02 | 2026-09-16 | 3 | 3 | Y | 9 | Moderate | Tier 1 | 2 | 4 | 2 | 4 | 4 | 4 | 3.3 | 2 | Yes | Medium | Monitor | P1 - This RICEFW is specific to MDG Create Material Workflow specific to Create PLAN, MAKE Stage Gates. Email notifications will be triggered based on MDG Personas. No automated alerts are configured. P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | MDG Team |  | Closed |  | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed
JGHJ-77804 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-77804 | Automation for JOM Chargebacks | Not a Common Object | WRICEF-NEW | Medium | Medium | Manjunath Baligeri | R2.2
JGHJ-36244 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Report | DEL-530 | Sales Order End-to-End Report | R1, R2.1 & R2.2 Common Object - DEL-530 | WRICEF-MODIFY | Medium | Medium | Vaishnav | R2.2
JGHJ-76345 | IMT-LOGISTICS | LOG_IO_TIME_IM | Interface | LOG-76345 | Outbound GR from S4 to GR in Atlas | Not a Common Object Earlier # SOU-76345 | WRICEF-NEW | Medium | Medium | Kumar maddela, Naveen | R2.2
JGHJ-36381 | IMT-LOGISTICS | LOG_IO_TIME_IM | Interface | DEL-292 | ASN Outbound- JJCC | R2.2 Common Object - LOG-55250, LOG-53889 | WRICEF-MODIFY | High | High | Gottipati, Buchi Babu | R2.2
JGHJ-55250 | IMT-LOGISTICS | LOG_IO_TIME_IM | Interface | LOG-55250 | Commercial-S4 to Steerling Integrator: EDI 856 - Outbound Interface - Outbound Delivery ASN | R2.1 & R2.2 Common Object - LOG-55250, LOG-53889 | WRICEF-MODIFY | High | High | Kumar maddela, Naveen | R2.2
JGHJ-36379 | IMT-LOGISTICS | LOG_IO_TIME_IM | Interface | DEL-236 | INTERIMREQ - Europe 2 to S4 - Inbound Interface - Inbound Delivery / PO Update | R1 & R2.2 Common Object - DEL-236, MAK-3006, MAK-3003 | WRICEF-MODIFY | High | High | Kumar maddela, Naveen | R2.2
JGHJ-76591 | IMT-RESEARCH_DEVELOPMENT | R&D_TIME_IM | Report | R&D-76591 | R & D - Study Master Export (with Unapproved Data) | With SAP | WRICEF-NEW | Medium | Medium | R&D Team | R2.2
JGHJ-68861 | IMT-RESEARCH_DEVELOPMENT | R&D_TIME_IM | Enhancement | R&D-68861 | R & D - Study Master | With SAP | WRICEF-NEW | High | High | R&D Team | R2.2
JGHJ-55133 | IMT-RESEARCH_DEVELOPMENT | R&D_TIME_IM | Enhancement | R&D-55133 | R & D - Study Master / E2E Study Report ( BTP ) | With SAP | WRICEF-NEW | High | High | R&D Team | R2.2
JGHJ-55132 | IMT-RESEARCH_DEVELOPMENT | R&D_TIME_IM | Interface | R&D-55132 | R & D Kit Type Interface to CTMS | With SAP | WRICEF-NEW | Medium | Medium | R&D Team | R2.2
JGHJ-55155 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-55155 | Error Monitor Enhancements | R2.1 & R2.2 Common Object - VCM-47421, VCM-55152, VCM-55155, VCM-76007 | WRICEF-MODIFY | High | High | Pravin Padwal | R2.2
JGHJ-50972 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-50972 | Outbound EDI 180 - Return Order Acknowledgment | Not a Common Object | WRICEF-NEW | Medium | Medium | Dinesh | R2.2
JGHJ-55248 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55248 | Clinical- Post Status Change interface to Non-SAP WMS - KDC | R2.2 Common Object - LOG-55248 & LOG-55249 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55249 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55249 | Clinical- Post Status Change interface to Non-SAP WMS - FDC | R2.2 Common Object - LOG-55248 & LOG-55249 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55100 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55100 | Clinical - Batch Master Data Interface - FDC | R2.2 Common Object - LOG-55100 & LOG-55101 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55101 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55101 | Clinical - Batch Master Data Interface - KDC | R2.2 Common Object - LOG-55100 & LOG-55101 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55226 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55226 | FDC-Outbound Interface for Clinical Master data from S4HANA to BY FDC ( Clinical R&D-Clinical Study Master/File SSKU) | R2.2 Common Object - LOG-55226, LOG-55238, LOG-55227, LOG-55239, LOG-55097 & LOG-55096 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55238 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55238 | FDC-Outbound Interface for Clinical Master Data from S4HANA to BY FDC ( Clinical R&D-Clinical Study Master File SKIT) | R2.2 Common Object - LOG-55226, LOG-55238, LOG-55227, LOG-55239, LOG-55097 & LOG-55096 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55227 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55227 | KDC-Outbound Interface for Clinical Master data from S4HANA to BY KDC ( Clinical R&D-Clinical Study Master/File SSKU) - ICSM VIews | R2.2 Common Object - LOG-55226, LOG-55238, LOG-55227, LOG-55239, LOG-55097 & LOG-55096 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55239 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55239 | KDC-Outbound Interface for Clinical Master Data from S4HANA to BY KDC ( Clinical R&D-Clinical Study Master File SKIT) | R2.2 Common Object - LOG-55226, LOG-55238, LOG-55227, LOG-55239, LOG-55097 & LOG-55096 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55097 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55097 | Clinical - Inbound Delivery Interface - KDC | R2.2 Common Object - LOG-55226, LOG-55238, LOG-55227, LOG-55239, LOG-55097 & LOG-55096 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55096 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55096 | Clinical - Inbound Delivery Interface - FDC | R2.2 Common Object - LOG-55226, LOG-55238, LOG-55227, LOG-55239, LOG-55097 & LOG-55096 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55220 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55220 | Clinical -Ext Wh EDI Integration (Non-SAP WMS) :- Internal WH Movement -Perform Physical Inventory (Quantity & Status) in Non-SAP WMS- KDC | R2.2 Common Object - LOG-55220 & LOG-55253 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55253 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55253 | Clinical :- Internal WH Movement -Perform Physical Inventory Adjustment (Quantity & Status) in Non-SAP WMS - FDC | R2.2 Common Object - LOG-55220 & LOG-55253 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55243 | IMT-LOGISTICS | INVM_TIME_IM | Enhancement | LOG-55243 | SBPA automation for shipping confirmation orchestration and error management | Not a Common Object | WRICEF-NEW | Medium | High | Amey/ Tilak | R2.2
JGHJ-47372 | IMT-LOGISTICS | INVM_TIME_IM | Enhancement | LOG-47372 | Commercial: Ext Wh (Non-SAP WMS) - Inventory Sync report | Not a Common Object | WRICEF-NEW | Critical | High | Amey/ Tilak | R2.2
JGHJ-52472 | IMT-LOGISTICS | INVM_TIME_IM | Enhancement | LOG-52472 | Clinical: Ext Wh (Non-SAP WMS) - Inventory Balance Sync report | Not a Common Object | WRICEF-NEW | High | High | Amey/ Tilak | R2.2
JGHJ-53889 | IMT-LOGISTICS | LOG_IO_TIME_IM | Interface | LOG-53889 | Outbound ASN Interface from TIME to ATLAS | R2.1 Common Object - LOG-55250, LOG-53889 | WRICEF-MODIFY | Medium | High | Kumar maddela, Naveen | R2.2
JGHJ-55251 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55251 | Clinical-Outbound Delivery Interface - FDC | R2.2 Common Object - LOG-55251 & LOG-55252 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55252 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55252 | Clinical-Outbound Delivery Interface - KDC | R2.2 Common Object - LOG-55251 & LOG-55252 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55246 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55246 | Clinical-Shipping Confirmation Interface (Goods Issue confirmation) - FDC | R2.2 Common Object - LOG-55246 & LOG-53824 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-53824 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-53824 | Clinical-Shipping Confirmation Interface (Goods Issue confirmation) - KDC | R2.2 Common Object - LOG-55246 & LOG-53824 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55147 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-55147 | Automation of Financial Flows - Scenario 3 (Push Scenario) - part of CR (1627, 1622 and 1628 Batch - 3 to 4 weeks - parallel work) + 1673 | Not a Common Object | WRICEF-NEW | High | High | Pravin Padwal | R2.2
JGHJ-76007 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-76007 | Non-VCA Monitor | R2.1 & R2.2 Common Object - VCM-47421, VCM-55152, VCM-55155, VCM-76007 | WRICEF-MODIFY | High | High | Pratiksha | R2.2
JGHJ-70303 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-70303 | AT additional 1 - Clinical AT | Not a Common Object | WRICEF-NEW | Medium | Medium | Rashmi Krishnappa | R2.2
JGHJ-50973 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-50973 | Inbound R & D - RTSM - Create Clinical Sales Orders | R2.1 & R2.2 Common Object - DEL-50973 | WRICEF-MODIFY | High | High | Firdaus | R2.2
JGHJ-47415 | IMT-LOGISTICS | TM_TIME_IM | Interface | LOG-47415 | TIME-L3-LOG-TM BY and XPS Integration: API for carrier label generation - KDC | R2.1 & R2.2 Common Object - LOG-47415 & LOG-55104 | WRICEF-MODIFY | Medium | High | Raghuma Busireddy | R2.2
JGHJ-55104 | IMT-LOGISTICS | TM_TIME_IM | Interface | LOG-55104 | TIME-L3-LOG-TM BY and XPS Integration: API for carrier label generation - FDC | R2.1 & R2.2 Common Object - LOG-47415 & LOG-55104 | WRICEF-MODIFY | Medium | High | Raghuma Busireddy | R2.2
JGHJ-55156 | IMT-VALUE_CHAIN | VCM_TIME_IM | Enhancement | VCM-55156 | Pre-requisite for API in Interfaces related to VCM | R2.1 & R2.2 Common Object - VCM-55156 | WRICEF-MODIFY | High | Complex | Pratiksha | R2.2
JGHJ-47413 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-47413 | Commercial-Shipping Confirmation Interface (Goods Issue confirmation) - KDC | Not a Common Object | WRICEF-NEW | Critical | High | Amey/ Tilak | R2.2
JGHJ-55245 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55245 | Commercial-Shipping Confirmation Interface (Goods Issue confirmation) - FDC | Not a Common Object | WRICEF-NEW | Critical | High | Amey/ Tilak | R2.2
JGHJ-47407 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-47407 | Commercial-Outbound Delivery Interface -KDC | R1 & R2.2 Common Object - DEL-002A, DEL-028, DEL-081, DEL-083, DEL-209, DEL-487, DEL-617, LOG-47407, LOG-57108, LLOG-47407 & LOG-51380 | WRICEF-MODIFY | Critical | High | Amey/ Tilak | R2.2
JGHJ-51380 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-51380 | Commercial-Outbound Delivery Interface - FDC | R1 & R2.2 Common Object - DEL-002A, DEL-028, DEL-081, DEL-083, DEL-209, DEL-487, DEL-617, LOG-47407, LOG-57108, LLOG-47407 & LOG-51380 | WRICEF-REUSE-EXTEND | Critical | High | Amey/ Tilak | R2.2
JGHJ-42586 | IMT-PLAN_SOURCE | SOURCE_TIME_IM | Interface | SOU-033 | Inbound interface to create PO in TIME for SO in Europe 2 | R1 & R2.2 Common Object - SOU-033, DEL-228 | WRICEF-MODIFY | Medium | Medium | Poman, Vikas | R2.2
JGHJ-51407 | IMT-PLAN_SOURCE | SOURCE_TIME_IM | Interface | SOU-51407 | Inbound Sales order interface from ATLAS to create PO in TIME - VMI Flow | R2.1 & R2.2 Common Object - SOU-51407 | WRICEF-MODIFY | Medium | Medium | Prasad, Vara | R2.2
JGHJ-51409 | IMT-PLAN_SOURCE | SOURCE_TIME_IM | Interface | SOU-51409 | Inbound Sales order interface from SUSTAIN to create PO in TIME - VMI Flow | R2.1 & R2.2 Common Object - SOU-51409 | WRICEF-MODIFY | Medium | Medium | Prasad, Vara | R2.2
JGHJ-51408 | IMT-PLAN_SOURCE | SOURCE_TIME_IM | Interface | SOU-51408 | Outbound PO interface from TIME to create SO in SUSTAIN | R2.1 & R2.2 Common Object - SOU-51406, SOU-514096 | WRICEF-MODIFY | Medium | Medium | Prasad, Vara | R2.2
JGHJ-51406 | IMT-PLAN_SOURCE | SOURCE_TIME_IM | Interface | SOU-51406 | Outbound PO interface from TIME to create SO in ATLAS | R2.1 & R2.2 Common Object - SOU-51406, SOU-514096 | WRICEF-MODIFY | Medium | Medium | Prasad, Vara | R2.2
JGHJ-51381 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-51381 | Clinical--Goods Receipt Interface - FDC | R2.2 Common Object - LOG-51381 & LOG-51382 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-51382 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-51382 | Clinical--Goods Receipt Interface - KDC | R2.2 Common Object - LOG-51381 & LOG-51382 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55242 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55242 | Clinical destruction order confirmation interface (BY>TIME)-FDC | Not a Common Object | WRICEF-NEW | Medium | High | Amey/ Tilak | R2.2
JGHJ-47412 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-47412 | Commercial-Material Master Data Interface/Product Dimensions - KDC | Not a Common Object | WRICEF-NEW | Critical | Complex | Amey/ Tilak | R2.2 | Integration (BTP IS) | LOG-MD-1 | 2026-09-08 | 3 | 3 |  | 9 | Moderate | Tier 2 | 4 | 4 | 2 | 4 | 4 | 4 | 3.7 | 2 | Yes | Medium | Monitor | P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | Project Team (Amey / Tilak) |  | Open | AMS Integration Lead | 2026-09-25 | 2026-09-30 | Pending | Pending | N
JGHJ-55102 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55102 | Commercial-Material Master Data Interface/Product Dimensions-FDC | Not a Common Object | No release build scope | Critical | Complex | Amey/ Tilak | R2.2 | Integration (BTP IS) | LOG-MD-1 | 2026-09-08 | 3 | 3 |  | 9 | Moderate | Tier 2 | 4 | 4 | 2 | 4 | 4 | 4 | 3.7 | 2 | Yes | Medium | Monitor | P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MDG Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | No runbook is defined for this RICEFW. | Project Team (Amey / Tilak) |  | Open | AMS Integration Lead | 2026-09-25 | 2026-09-30 | Pending | Pending | N
JGHJ-55098 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55098 | Clinical-Material Master Data Interface/Product Dimensions - ICSM Views - KDC | R2.2 Common Object - LOG-55098 & LOG-53819 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2 | Integration (BTP IS) | LOG-MD-1 | 2026-09-08 | 2 | 3 |  | 6 | Low | Tier 3 | 4 | 4 | 2 | 4 | 4 | 1 | 3.2 | 1 | Yes | Medium | Controlled | P3/P6: AMS support readiness is not fully established. Operational support documentation (Runbook/DOU/RACI) has not been validated with AMS, and AMS does not currently have the required access to support and monitor the interface independently.Complexity:3: There is a dependency on the action taken furing a failure on Technical team to reprocess the failures and not sure whether they have covered this in their KT so far. | Project team to provide validated Runbook/DOU/RACI, escalation matrix, and complete AMS access provisioning and validation for all required monitoring and support applications before Hypercare handover. | Integration Team |  |  | AMS Integration Lead | 2026-09-25 | 2026-09-30 | Pending | Pending | N
JGHJ-53819 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-53819 | Clinincal-Material Master Data Interface/Product Dimensions - FDC | R2.2 Common Object - LOG-55098 & LOG-53819 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2 | Integration (BTP IS) | LOG-MD-1 | 2026-09-08 | 2 | 3 |  | 6 | Low | Tier 3 | 4 | 4 | 2 | 4 | 4 | 4 | 3.7 | 2 | Yes | Medium | Controlled | P3/P6: AMS support readiness is not fully established. Runbook/DOU validation has not been completed and AMS does not currently have the required access to independently support and monitor the interface.Complexity:3: There is a dependency on the action taken furing a failure on Technical team to reprocess the failures and not sure whether they have covered this in their KT so far. | Project team to provide validated Runbook/DOU, support procedures, escalation matrix, and complete AMS access provisioning and validation before Hypercare handover. | Integration Team |  |  | AMS Integration Lead | 2026-09-25 | 2026-09-30 | Pending | Pending | N
JGHJ-47408 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-47408 | Commercial-Goods Receipt Interface - KDC | R2.2 Common Object - LOG-47408 & LOG-55254 | WRICEF-MODIFY | Critical | Complex | Amey/ Tilak | R2.2
JGHJ-55254 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55254 | Commercial-Goods Receipt Interface - FDC | R2.2 Common Object - LOG-47408 & LOG-55254 | WRICEF-REUSE-EXTEND | Critical | Complex | Amey/ Tilak | R2.2
JGHJ-47405 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-47405 | Commercial-Inbound Delivery Interface - KDC | Not a Common Object | WRICEF-NEW | Critical | Complex | Amey/ Tilak | R2.2
JGHJ-55218 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55218 | Commercial-Inbound Delivery Interface - FDC | Not a Common Object | No release build scope | Critical | Complex | Amey/ Tilak | R2.2
JGHJ-55237 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55237 | Commercial-Ext Wh EDI Integration (Non-SAP WMS) :- Internal WH Movement -Perform Physical Inventory (Quantity & Status) in Non-SAP WMS- KDC | R2.2 Common Object - LOG-55237 & LOG-55247 | WRICEF-MODIFY | Critical | High | Amey/ Tilak | R2.2
JGHJ-55247 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55247 | Commercial :- Internal WH Movement -Perform Physical Inventory Adjustment (Quantity & Status) in Non-SAP WMS - FDC | R2.2 Common Object - LOG-55237 & LOG-55247 | WRICEF-REUSE-EXTEND | Critical | High | Amey/ Tilak | R2.2
JGHJ-55256 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55256 | Commercial - Post Status Change interface to Non-SAP WMS - KDC | R2.2 Common Object - LOG-55256 & LOG-55257 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-55257 | IMT-LOGISTICS | INVM_TIME_IM | Interface | LOG-55257 | Commercial - Post Status Change interface to Non-SAP WMS - FDC | R2.2 Common Object - LOG-55256 & LOG-55257 | WRICEF-MODIFY | High | High | Amey/ Tilak | R2.2
JGHJ-67164 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-67164 | EDI 810 S4 Outbound Invoice - IBM Sterling | R1, R2.1 & R2.2 Common Object - DEL-6716, DEL-67164, DEL-52182, DEL-50974 & DEL-67403 | WRICEF-MODIFY | Medium | Medium | Dinesh | R2.2
JGHJ-52182 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-52182 | Outbound EDI 812 - Credit/Debit adjustment for Returns | R2.2 Common Object - DEL-67164, DEL-52182, DEL-50974 & DEL-67403 | WRICEF-MODIFY | Medium | Medium | Dinesh | R2.2
JGHJ-50974 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-50974 | S4 to Atlas - Outbound Interface - Invoicing | R2.2 Common Object - DEL-67164, DEL-52182, DEL-50974 & DEL-67403 | WRICEF-MODIFY | Medium | Low | Firdaus | R2.2
JGHJ-67403 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-67403 | Inbound Return Order Creation based on trigger from Blue Yonder for FDC | R2.2 Common Object - DEL-67164, DEL-52182, DEL-50974 & DEL-67403 | WRICEF-MODIFY | Medium | Medium | Quinn | R2.2
JGHJ-36522 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | MD-0426 | Outbound Interface for Customer Master data to Contact Center Case Mgm SFDC | R1, R2.1 & R2.2 Common Object - MD-0426, MD-0411 | WRICEF-MODIFY | Medium | Medium | Dinesh | R2.2
JGHJ-50976 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-50976 | Atlas to S4 - Inbound Order Create Interface - PO to SO | R1, R2.1 & R2.2 Common Object - DEL-50976, DEL-50976, DEL-77805, DEL-77805, DEL-78693, DEL-57110, DEL-67163 & DEL-51405 | WRICEF-MODIFY | Medium | Low | Firdaus | R2.2
JGHJ-77805 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-77805 | Chargeback Credit/Debit memo request creation | R2.2 Common Object - DEL-50976, DEL-77805, DEL-77805, DEL-78693, DEL-57110, DEL-67163 & DEL-51405 | WRICEF-MODIFY | Medium | Medium | Setu | R2.2
JGHJ-78693 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-78693 | Europe2 Delivery Note to SO in TIME - Inbound Interface R2.2 | R2.2 Common Object - DEL-50976, DEL-77805, DEL-77805, DEL-78693, DEL-57110, DEL-67163 & DEL-51405 | WRICEF-MODIFY | Medium | Medium | Dinesh | R2.2
JGHJ-57110 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-57110 | Inbound Return Order Creation based on trigger from Blue Yonder for KDC | R2.2 Common Object - DEL-50976, DEL-77805, DEL-77805, DEL-78693, DEL-57110, DEL-67163 & DEL-51405 | WRICEF-MODIFY | Medium | Medium | Dinesh | R2.2
JGHJ-67163 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-67163 | Inbound Sales Order from Partner EDI (EDI 850) - IBM Sterling | R2.2 Common Object - DEL-50976, DEL-77805, DEL-77805, DEL-78693, DEL-57110, DEL-67163 & DEL-51405 | WRICEF-MODIFY | Medium | Medium | Dinesh | R2.2
JGHJ-51405 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-51405 | Inbound EDI 180 - Return Order Create | R2.2 Common Object - DEL-50976, DEL-77805, DEL-77805, DEL-78693, DEL-57110, DEL-67163 & DEL-51405 | WRICEF-MODIFY | Medium | Medium | Dinesh | R2.2
JGHJ-36260 | IMT-PLAN_SOURCE | SOURCE_TIME_IM | Interface | SOU-603 | Outbound Interface from Time S/4 to EU2 for the IC Sales Order Creation | R1 & R2.2 Common Object - DEL-603, SOU-603 | WRICEF-MODIFY | Medium | Medium | Poman, Vikas | R2.2
JGHJ-36533 | IMT-PLAN_SOURCE | PLAN_TIME_IM | Interface | PLA-0027 | Sending Artwork data between Atlas , B2B & EU2 systems | R1 & R2.2 Common Object - PLA-0027 | WRICEF-MODIFY | High | High | Solanki, Abhimanyu | R2.2
JGHJ-36424 | IMT-MASTER_DATA | MDG_TIME_IM | Interface | FIN-0039B | Inbound Interface from Lynx for Vendor Information (MD) | R1, R2.1 & R2.2 Common Object - FIN-0039B | WRICEF-MODIFY | Medium | Medium | Harsh Arora/Prajakta | R2.2
JGHJ-94545 | IMT-PLAN_SOURCE | SOURCE_TIME_IM | Enhancement | SOU-94545 | Copy "Origin Acceptance" Indicator in PO from Contracts | Not a Common Object | WRICEF-NEW | Medium | Medium | Prasad, Vara | R2.2
JGHJ-36272 | IMT-MAKE | MAKE-QM | Enhancement | MAK-1002 | Batch Number Generation | R1, R2.2 & R3.1 Common Object - MAK-1002 | WRICEF-MODIFY-EXTEND | Medium | Medium | Jayavibhava | R2.2 | Enhancement | QM KT-01 | 2026-09-17 | 2 | 2 |  | 4 | Low | Tier 3 | 2 | 4 | 4 | 3 | 4 | 4 | 3.5 | 2 | Yes | Medium | Controlled | P1-- Still no automatic alert mechanism (e.g mail notification for failure) is available. |  | Project Team(Sharma, Brajesh) |  | Open | AMS Lead(Shashi) | 2026-09-28 | 2026-10-01 | Pending | Deemed confirmed | N
JGHJ-55145 | IMT-VALUE_CHAIN | VCM_TIME_IM | Report | VCM-55145 | FI report to show goods movement + Value | R2.1 & R2.2 Common Object - VCM-47421, VCM-55155, VCM-76007 | WRICEF-MODIFY | High | Complex | Manjunath Baligeri | R2.2
JGHJ-111454 | IMT-MASTER_DATA | MDG_TIME_IM | Enhancement | MDG-C-111454 | MDG-C: Functional Module for DQM Restrictions for Interface Scenarios | Not a Common Object | WRICEF-NEW | Medium | Medium | Poorna | R2.2 | Enhancement | KT-02 | 2026-09-09 | 2 | 2 |  | 4 | Low | Tier 3 | 2 | 4 | 2 | 4 | 4 | 4 | 3.3 | 2 | Yes | Medium | Controlled | TBD | TBD
JGHJ-36383 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Interface | DEL-294 | Inbound Sales Order from Partner EDI (EDI 850) - IBM Sterling | R1 Common Object - DEL-293, DEL-294, DEL-494, DEL-435, DEL-434, DEL-432, DEL-431, DEL-235, DEL-605 | WRICEF-MODIFY-EXTEND | Low | Low | Dinesh aitha, Sai [JANUS NON-J&J] | R2.2
JGHJ-46466 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Enhancement | DEL-90205 | CE_DTP_FTP orders address override BADI enhancement | Not a Common Object | WRICEF-NEW | Medium | Medium | Dhaval | R2.2
JGHJ-36211 | IMT-PLAN_SOURCE | PLAN | Enhancement | PLA-0067 | Splitting of Demands for Planning in APS | R1 & R2.2 Common Object - PLA-0067 | WRICEF-MODIFY | High | High | Satish Koppuravuri | R2.2
JGHJ-90599 | IMT-DELIVER | CONT_PRC_OM_TIME_IM | Enhancement | DEL-90599 | TIME-L3-CEX-CE Enhancement for Debit/Credit Memo with Reference Pricing | Operate & R2.2 Common Object - PLA-0067 | WRICEF-NEW | High | High | Satish Koppuravuri | R2.2
JGHJ-46464 | IMT-MAKE | QUALITY_TIME_IM | Enhancement | MAK-46464 | BOM-FID Packaging Component Compliance Check | Not a Common Object | WRICEF-NEW | High | High | Raho, Giusy | R2.2 | Integration (BTP IS) | QM KT-01 | 2026-09-17 | 3 | 3 |  | 9 | Moderate | Tier 2 | 2 | 4 | 2 | 4 | 4 | 1 | 2.8 | 1 | Yes | Low | Mitigation required | P1-- Still no automatic alert mechanism (e.g mail notification for failure) is available. P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MAKE Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. P6- Still AMS donot have respective CAPM App access in DJS | 1.Project team can provide the Mail notification mechanism in BTP for any failure if its missed to update in report 2. runbook need to defined for this RICEFW. | Project Team(Raho, Giusy) |  | Open | AMS Lead(Shashi) | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed | N
JGHJ-36274 | IMT-MAKE | QUALITY_TIME_IM | Enhancement | MAK-1005 | Quality Checks at usage decision or batch status- stock status change | R1 & R2.2 Common Object - MAK-1005 | WRICEF-MODIFY | Medium | Medium | Sharma, Brajesh | R2.2 | Enhancement | QM KT-03 | 2026-09-23 | 3 | 2 |  | 6 | Low | Tier 3 | 2 | 4 | 2 | 4 | 4 | 4 | 3.3 | 2 | Yes | Medium | Controlled | P1- Still no automatic alert mechanism (e.g. Monitoring Design for failure) is available. P3 - No runbook is maintained for this RICEFW. AMS Team will follow the MAKE Deliverables tracker followed by traceability matrix which includes the FS/TS design documents and JIRA BUS/TUS. | 1.Project team can provide the mechanism design if the enhancement didn't give relevant error or warning message for missing information during usage decision. 2. Runbook need to defined for this RICEFW. | Project Team(Sharma, Brajesh) |  | Open | AMS Lead(Shashi) | 2026-09-25 | 2026-09-30 | Pending | Deemed confirmed | N
Formulas:
Project Response Due = IF(ISNUMBER([AMS Scored On]),WORKDAY([AMS Scored On],3),"")
Effective Project Status = IF([Project Status]="","",IF(AND([Project Status]="Pending",ISNUMBER([Project Response Due]),TODAY()>[Project Response Due]),"Deemed confirmed",[Project Status]))